## Sprint Backlog (Scrum)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment
CM_01 | US:101 | 1 | Update Customer Information | Divya,Harini | 2020-07-14 | 4 hour | 3 hour | Completed
CM_02 | US:102 | 1 | Add Books | V.Supriya | 2020-07-14 | 4 hour | 3 hour | Completed
CM_03 | US:103 | 1 | Remove Books | D.Shravya | 2020-07-14 | 4 hour | 3 hour | Completed
CM_04 | US:104 | 1 | Update quantity | Prateek Panday,Hemant Kumar | 2020-07-14 | 4 hour | 3 hour | Completed
RM_01 | US:105 | 1 | List all orders | Saketh Reddy | 2020-07-14 | 4 hour | 3 hour | Completed
RM_02 | US:106 | 1 | view order details | Arun Kumar | 2020-07-14 | 4 hour | 3 hour | Completed
RM_03 | US:107 | 1 | Delete an order | Deepak Bharti | 2020-07-14 | 4 hour | 3 hour | Completed

## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Work Product Cross Reference/Details sheet | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | CM_01 | List all orders | M | US: 101 | to display all the orders placed by the customers | Admin | Order management | medium | Analysing the workflow of project | Refered the case studies provided in the documents | Admin can view all the orders placed by the customers. | [5 empty] | required |  | This is used to view all the orders placed by the customers
2 | CM_02 | view order details | M | US: 102 | Displaying the particular order details | Admin | Order management | medium | Analysing the workflow of project to diplay the details of particular order | Refered the case studies provided in the documents | Admin can view the particular order placed by the customer. | [5 empty] | required |  | This is used to view particular order details
3 | CM_03 | delete an order | M | US: 103 | deleting an order | Admin | Order management | medium | Analysing the workflow of project to delete an order | Refered the case studies provided in the documents | Admin can login and delete the order | [5 empty] | required |  | This is used to delete an order placed by the customer
4 | CM_04 | update customer information | M | US: 104 | updating the customer information | Admin | Order management | medium | Analysing the workflow of project to update the customer information | Refered the case studies provided in the documents | A customer can update his/her details . | [5 empty] | required |  | This isused to update the customer information.
5 | CM_05 | add books | M | US: 105 | to add books | Admin | Order management | medium | Analysing the workflow of project and to add books | Refered the case studies provided in the documents | Admin can add new books to the list. | [5 empty] | required |  | This is used to update books
6 | CM_06 | remove books | M | US: 106 | To delete the books | Admin | Order management | medium | Analysing the workflow of project to remove the books | Refered the case studies provided in the documents | Admin can remove the books from the list. | [5 empty] | required |  | This is used to delete books
7 | CM_07 | Update quantity | M | US: 107 | to update the quantity of the books | Admin | Order management | medium | Analysing the workflow of project to update the quantity of books in the list | Refered the case studies provided in the documents | Admin can update the quantity of books in the list. | [5 empty] | required |  | This is used to update the quantity of the books in the list.